# ADDENDUM No. 2 TO THE FINANCING AGREEMENT

Framework Programme in support of the current and new agreements between the European Union and the Republic of Moldova

# ENPI/2012/023-421

# Special Conditions

The European Commission, hereinafter referred to as "the Commission", acting on behalf of the European Union, hereinafter referred to as "the EU",

of the one part, and

the Republic of Moldova, represented by the Government of the Republic of Moldova, hereinafter referred to as "the Beneficiary",

of the other part,

have agreed as follows:

The following provisions of Financing Agreement for the Programme "Framework Programme in support of the current and new agreements between the European Union and the Republic of Moldova" which entered into force on 12 December 2013, as amended by Addendum No.1 entered into force on 25 August 2014, are hereby modified as follows:

ARTICLE 5 – PERIOD OF EXECUTION

"5.1	The period of execution of the Financing Agreement as defined in Article 4 of the General Conditions shall commence on the entry into force of the Financing Agreement and end 87 months after this date.

5.2	The duration of the operational implementation phase is fixed at 63 months.

5.3	The duration of the closure phase is fixed at 24 months.

ARTICLE 7 – ANNEXES

The new version of Annex II "Technical and Administrative Provisions" is attached to this addendum.

MODIFICATION OF THE BUDGET OF THE FINANCING AGREEMENT

|  | EU contribution in EUR million |
| --- | --- |
| Categories | Budget after Addendum No.1 | Budget after Addendum No.2 |
| Components 1,2 and 3 | 19.0 | 22.0 |
| Component 4 | 8.54 | 8.54 |
| Component 5 | 4.8 | 1.8 |
| External Evaluation and Audit | 0.2 | 0.2 |
| Total | 32.54 | 32.54 |

All other terms and conditions of the Financing Agreement and its previous addendum, including Logical Framework, remain unchanged.

This Addendum shall form an integral part of the Financing Agreement and shall enter into force on the date on which the Commission receives a notification from the Beneficiary confirming the completion of the internal procedures of the Beneficiary necessary for its entry into force. The Commission shall inform the Beneficiary of the date of the receipt of this notification.

Done in English in two original copies, one copy being handed to the Commission and one to the Beneficiary.

| FOR THE COMMISSION | FOR THE BENEFICIARY |
| --- | --- |
| Lawrence MEREDITH Director Neighbourhood East Directorate-General for Neighbourhood and Enlargement Negotiations Signature: Date: | Prime Minister Government of the Republic of Moldova Signature: Date: |